## Sheet1
PLLF tracker
problem | Raised by | Noted | action | date
change n() to n_eval() | Patrick | 2025-05-29 | done | 2025-06-18
For profile(), the results are reported on the log scale, even when cmd uses eform. | Ian | 2025-05-29 | done, but check my defaults and add to help | 2025-06-18
Verbose option to show ML output | Patrick | 2025-05-29 | done | 2025-06-18
Allow profile(_cons)? | Ian | 2025-05-29 | done | 2025-06-18
rmcoll routine causes SE not found error | Ian | 2025-05-29 | rmcoll routine removed | 2025-06-18
Update help file | Ian | 2025-05-29 | done | 2025-07-18
"Handling 'equations' correctly" section of help file seems to be wrong. Certainly -pllf, profile(x): poisson x, exposure()- works | Ian | 2025-05-29 | remove from help | 2025-08-01
Create some data that can be analysed in the help file, containing variables count and group | Ian | 2025-05-29 | added to help file | 2025-06-18
use_deviance. Ian: only defined in the profile() part, so I removed it from formula(). Shoud it instead have been defined also for formula()? Patrick: Not sure. Suggest putting this on the back burner with the code as in the original version. It may turn up again with more intensive testing or use (?). | Ian | 2025-05-29 | tbd later
Make it work with perfect prediction | Ian | <05/2025 | done | <18/06/2025
if SE not found, range becomes (b,b) | Ian | 2025-06-18 | issue error instead | 2025-06-18
collinearity needs new handling: e.g. -pllf, profile(group) : poisson events group group- fails, as does -pllf, profile(group) : poisson events group group2- if group2==group | Ian | 2025-06-18 | done | 2025-07-23
When profile() contains an eqname, a different method is used, via constraints. Can we harmonise? | Ian | 2025-06-18 | not sure; seem to give same answer; but constraint is faster!
add Normal approximation to PLLF graph? | Ian | 2025-06-18 | yes worth doing: -shownormal- option | 2025-08-01
make repo public | Ian | 2025-07-18 | done | 2025-09-01
need help file example for syntax 2 | Ian | 2025-07-30 | done | 2025-08-01
change !mi to !missing passim | Patrick | 2025-07-30 | done | 2025-08-01
syntax 1 example for profiling constant - use brca data | Ian | 2025-07-30 | done | 2025-08-01
document mleline and DROPCollinear | Ian | 2025-07-30 | done | 2025-08-01
authors: Patrick, Ian, Ian email | Ian | 2025-07-30 | done | 2025-08-01
find example for syntax 1: TBCHAMP / TRISST - to help file? | Patrick | 2025-07-30 | and use in talk! | 2025-08-01
does pllf handle break correctly? | Ian | 2025-07-31 | yes - no action needed | 2025-08-01
should the last estimation command be dropped from memory? | Ian | 2025-08-01 | ereturn clear | 2025-09-01
save the normal approx to data | Ian | 2025-08-05 | done | 2025-09-01
change first help file example from 38-19 to 8-3 | Ian | 2025-08-14 | done | 2025-09-01
Improve "Stored results" section - to be like -h regress-? | Ian | 2025-08-14 | done | 2025-09-01
Improve help file by showing both syntaxes in the syntax diagram, thus also explaining what pllf does; changing the RHS of the syntax diagram to just regression_cmd | Ian | 2025-08-14 | done | 2025-09-01
Syntax 2: Remove the placeholder X from regression_cmd; make the default placeholder(@) | Ian | 2025-08-14 | done | 2025-09-01
test pllf when there are interactions in the model | Ian | 2025-08-19 | it only works at present using xi
why are the Pearce and Venzon references in the help file? Omit? | Ian | 2025-09-03
capture "convergence not achieved" and just print a red "x" instead of green dot; also somehow flag the _pll output | Ian | 2025-09-16
there's a lot of duplicated code in there! | Ian | 2025-09-16
Need a note that robust/cluster options are ignored (from Stephen Jenkins' Q at Stata UG) | Ian | 2025-09-19