## Sheet1
PLLF tracker
problem | Raised by | Noted | action | date
if SE not found, range becomes (b,b) | Ian | 2025-06-18 | issue error instead | 2025-06-18
rmcoll routine causes SE not found error | Ian | 2025-06-18 | rmcoll routine removed | 2025-06-18
change n() to n_eval() | Patrick | 2025-05-29 | done | 2025-06-18
For profile(), the results are reported on the log scale, even when cmd uses eform. | Ian | 2025-05-29 | done, but check my defaults and add to help | 2025-06-18
Verbose option to show ML output | Patrick | 2025-05-29 | done | 2025-06-18
Allow profile(_cons)? | Ian | 2025-05-29 | done | 2025-06-18
Improve -rmcoll-: drop altogether or make noRMcoll the default? | Ian | 2025-05-29 | At present it drops x's that are collinear with y, which is wrong e.g. for analysis of 2x2 table
Update help file | Ian | 2025-05-29 | done | 2025-07-18
"Handling 'equations' correctly" section of help file seems to be wrong. Certainly -pllf, profile(x): poisson x, exposure()- works | Ian | 2025-05-29 | ask Patrick
Create some data that can be analysed in the help file, containing variables count and group | Ian | 2025-05-29 | added to help file | 2025-06-18
use_deviance. Ian: only defined in the profile() part, so I removed it from formula(). Shoud it instead have been defined also for formula()? Patrick: Not sure. Suggest putting this on the back burner with the code as in the original version. It may turn up again with more intensive testing or use (?). | Ian | 2025-05-29
Make it work with perfect prediction | Ian | <05/2025 | done | <18/06/2025
When profile() contains an eqname, a different method is used, via constraints. Can we harmonise? | Ian | 2025-06-18
collinearity needs new handling: e.g. -pllf, profile(group) : poisson events group group- fails, as does -pllf, profile(group) : poisson events group group2- if group2==group | Ian | 2025-06-18 | discuss
add Normal approximation to PLLF graph? | Ian | 2025-06-18
make repo public | Ian | 2025-07-18