## Sheet1
PLLF tracker
problem | Raised by | Noted | action | date
change n() to n_eval() | Patrick | 2025-05-29 | done | 2025-06-18
For profile(), the results are reported on the log scale, even when cmd uses eform. | Ian | 2025-05-29 | done, but check my defaults and add to help | 2025-06-18
Verbose option to show ML output | Patrick | 2025-05-29 | done | 2025-06-18
Allow profile(_cons)? | Ian | 2025-05-29 | done | 2025-06-18
rmcoll routine causes SE not found error | Ian | 2025-05-29 | rmcoll routine removed | 2025-06-18
Update help file | Ian | 2025-05-29 | done | 2025-07-18
"Handling 'equations' correctly" section of help file seems to be wrong. Certainly -pllf, profile(x): poisson x, exposure()- works | Ian | 2025-05-29 | remove from help | 2025-08-01
Create some data that can be analysed in the help file, containing variables count and group | Ian | 2025-05-29 | added to help file | 2025-06-18
use_deviance. Ian: only defined in the profile() part, so I removed it from formula(). Shoud it instead have been defined also for formula()? Patrick: Not sure. Suggest putting this on the back burner with the code as in the original version. It may turn up again with more intensive testing or use (?). | Ian | 2025-05-29 | tbd later
Make it work with perfect prediction | Ian | <05/2025 | done | <18/06/2025
if SE not found, range becomes (b,b) | Ian | 2025-06-18 | issue error instead | 2025-06-18
collinearity needs new handling: e.g. -pllf, profile(group) : poisson events group group- fails, as does -pllf, profile(group) : poisson events group group2- if group2==group | Ian | 2025-06-18 | done | 2025-07-23
When profile() contains an eqname, a different method is used, via constraints. Can we harmonise? | Ian | 2025-06-18 | not sure; seem to give same answer; but constraint is faster!
add Normal approximation to PLLF graph? | Ian | 2025-06-18 | yes worth doing: -shownormal- option | 2025-08-01
make repo public | Ian | 2025-07-18 | yes
need help file example for syntax 2 | Ian | 2025-07-30 | done | 2025-08-01
change !mi to !missing passim | Patrick | 2025-07-30 | done | 2025-08-01
syntax 1 example for profiling constant - use brca data | Ian | 2025-07-30 | done | 2025-08-01
document mleline and DROPCollinear | Ian | 2025-07-30 | done | 2025-08-01
authors: Patrick, Ian, Ian email | Ian | 2025-07-30 | done | 2025-08-01
find example for syntax 1: TBCHAMP / TRISST - to help file? | Patrick | 2025-07-30 | and use in talk! | 2025-08-01
does pllf handle break correctly? | Ian | 2025-07-31 | yes - no action needed | 2025-08-01
should the last estimation command be dropped from memory? | Ian | 2025-08-01 | Reload the model with the selected parameter value (MLE) and leave that model in memory. If there is no such value we just leave nothing via ereturn clear.
save the normal approx to data? | Ian | 2025-08-05 | discuss
change first help file example from 38-19 to 8-3 | Ian | 2025-08-14
Improve "Stored results" section - to be like -h regress-? | Ian | 2025-08-14
Improve help file by showing both syntaxes in the syntax diagram, thus also explaining what pllf does; changing the RHS of the syntax diagram to just regression_cmd | Ian | 2025-08-14
Syntax 2: Remove the placeholder X from regression_cmd; make the default placeholder(#) | Ian | 2025-08-14
test pllf when there are interactions in the model | Ian | 2025-08-19